## Form 6 (1st Q 2019)
FDP Form 6 - Trust Fund Utilization | [8 empty] | October
November
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES | [8 empty] | December
For the 1st Quarter, CY 2019
Province, City or Municipality: ALAMINOS, LAGUNA
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DSWD - Region IV-A (Senior Citizen Pension) | LGU-Alaminos | 1920000 | 2018-11-27 |  | 100% | 1920000 |  | 0 | 100%
DSWD - Region IV-A (Supplemental Feeding Program) | LGU-Alaminos | 1566000 | 2018-06-22 |  | 62.5% | 978724 |  | 587276 | 62.5% | 1251154.5 | 314845.5
DSWD -Region IV-A (Sustainable Livelihood Program) | LGU-Alaminos | 5095341.25 | 2017-11-16 |  | 66.36% | 3381308.5 |  | 1714032.75 | 66.36% | 1938892.75 | 3156448.5
DTI Region IV-A (Yaman Pinoy) | LGU-Alaminos | 1000000 | 2017-09-22 |  | 60.61% | 606077 |  | 393923 | 60.61% | 716450 | 283550
DILG Region IV-A (LGSF-DepEd) | LGU-Alaminos | 4725000 | 2016-01-12 |  | 100% |  |  | 4725000 | 0%
DILG Region IV-A (Assistance to Municipalities) AM | LGU-Alaminos | 9168580 | 2018-09-03 |  | 0% | 0 |  | 9168580 | 0%
DILG Region IV-A (Assistance to Disadvantage Municipalities) ADM | LGU-Alaminos | 16729000 | 2016-08-30 |  | 7% |  |  | 16729000 | 0%
TOTAL |  | 25897580 |  |  |  | 0 |  | 25897580
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| CIRILO M. MISTA |  |  |  |  | HON. LORETO M. MASA
| Municipal Accountant |  |  |  |  | LCE
100
DOH Region IV-A | LGU-Alaminos | 2000000 | 2016-06-29 |  | 90.39% | 1807755 |  | 192245